## Lam
User ID | Name
40238338 | Tung Lam Ha
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-30 |  |  | 60 | Research on backend framework
2025-01-31 |  |  | 90 | Meeting #1
2025-01-31 |  |  | 15 | Creation of organization and github repository
2025-02-05 | 19:00 |  | 45 | Have team meeting #2 and taking meeting minutes
2025-02-06 | 23:00 | #9 & #10 | 240 | Dashboard UI side bar and message board
2025-02-07 | 13:00 | 7 & 9 | 45 | Merge Login UI and Dashboard UI

## Gilbert
User ID | Name
40115222 | Gilbert Sedillo
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-29 | 17:00 | N/A | 0.75 | Research on front end technologies
2025-01-31 | 17:00 | N/A | 1.5 | Meeting #1
2025-02-05 | 19:00 | N/A | 0.75 | Team meeting #2
2025-02-06 | 19:00 | #12 | 4 | Distinguish user roles (Task 6) | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/issues/12

## Tony
User ID | Name
40255597 | Ming-Hung Kao
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-02-03 |  | N/A | 0.25 | Push frontend code to Github
2025-02-04 |  | #15 | 3 | Design the front end UI for the system | https://youtu.be/SqcY0GlETPk?si=KRnOMasw4xoiUfz3
2025-02-05 |  | #16 | 0.1 | Create a project on firebase
2/6/0225 |  | #6 | 1 | Merge code from Lam to the UI I built

## Jeff
User ID | Name
40283099 | Jeff Zhong
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-30 | 17:00 | N/A | 0.25 | I made a discord for the entire group so we can communicate, I also asked the professor for extra information in regards of the project
2025-02-04 | 18:00 | #8 | 6 | First template of the website has been made. The login system and dashboard has been created with a tutorial | Link to the tutorial: https://www.youtube.com/watch?v=2hR-uWjBAgw
2025-02-05 | 20:00 | #6 | 3 | Made a functionning role system | Based on this tutorial: https://www.youtube.com/watch?v=0gLr-pBIPhI
2025-02-06 | 18:00 | N/A | 0.5 | Adjust GitHub details and make user stories more detailled
2025-02-06 | 19:00 | N/A | 0.5 | Make the tasks for the team to work on. Added despcriptions
WRITE AN EMAIL ABOUT THE SCRUM MEETING
I did the template and setting up the firestore base. I also made the firebas ething work with the authentication with the email and password. I made a small tempalte using simple javascript. Next week I will work on the users being able to be dragged into a text channel
WRITE AN EMAIL WHEN YOU COMPLETE the TEXT CHANNEL cREATION + ADD A TICKET ON GITHUB

## Nav
User ID | Name
40129282 | Navraj Jhajj
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-02-01 | 18:00 | NA | 1.5 hours | (first time learning to code frontend)
2025-02-06 | 18:00 | #13 | 3 hours | Adapting to github, made this longer than it should.