## Sprint 1
Issue # | User Story Title/Task Title | Story Points (hours) | Due Date | Description/Associated Tasks | Difficulty Level (0,1,2,3,4,5) | Priority | Risk | Assign | Sprint
6 | US-1 - Build User Authentication | 10 | 2025-02-07 | As a user, I want to be able to login to the system so that I can access the dashboard. | 3 | 1 | Low | Jeff, Tony, Gilbert, Nav | 1
7 | US-2 - Build Frontend with React | 3 | 2025-02-07 | As a user, I want to be able to interact with the system so that I can navigate and understand the system better. Related to #15 | 2 | 3 | Medium | Lam, Tony | 1
8 | US-3 - Build Dashboard | 4 | 2025-02-07 | As a User, after signing in the system, I want to be able to access the dashboard and see my name | 2 | 2 | Medium | Lam | 1
12 | Task 6 - Distinguish a user and an Admin | 4 | 2025-02-07 | When you are authenticated, make the system recognize the Admin vs the user. | 4 | 1 | Low | Gilbert | 1
13 | Task 5 - Error handling | 2 | 2025-02-07 | Make a proper error statement if the username does not exist. | 2 | 3 | Low | Nav | 1
14 | Task 4 - Registering a new user | 1.5 | 2025-02-07 | Make a button to register a user in case the user does not exist. When the user registers, the user can enter their email and password. The information should store into a database where their account will be saved. | 2 | 4 | High | Jeff, Tony | 1
15 | Task 7 - Make Login interface | 1 | 2025-02-07 | Make the graphical interface user-friendly. Must be able to distinguish each element (login vs. register) and distinguish the various fields (email vs password) | 1 | 2 | Medium | Tony | 1
8 | Task 1 - Missing graphic interface | 3 | 2025-02-07 | Make a proper graphic interface for the dashboard. It needs to be easy to follow and navigate. | 1 | 3 | Medium | Lam | 1
10 | Task 2 - Missing Role specification on Dashboard | 2 | 2025-02-07 | The dashboard displays the role of the user when they log-in. The role options that are displayed are users and admins. The role is displayed right under the user's name. | 2 | 1 | Low | Jeff, Gilbert | 1
19 | Task 9 - Display user's login information | 0.5 | 2025-02-07 | When the user logs into the system, they can see their email displayed. | 2 | 2 | Low | Jeff | 1

## Sprint 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,4,5) | Priority | Risk | Assign | Sprint
6 | US-1 - Build User Authentication | As a user, I want to be able to login to the system so that I can access the dashboard. | 3 | 1 | No | Jeff, Tony, Gilbert, Nav | 1
7 | US-2 - Build Frontend with React | As a user, I want to be able to interact with the system so that I can navigate and understand the system better. | 2 | 3 | Yes | Lam, Tony | 1
8 | US-3 - Build Dashboard | As a User, after signing in the system, I want to be able to access the dashboard and see my name | 2 | 2 | Yes | Lam | 1
12 | Task 6 - Distinguish a user and an Admin | When you are authenticated, make the system recognize the Admin vs the user. | 4 | 1 | No | Gilbert | 1
13 | Task 5 - Error handling | Make a proper error statement if the username does not exist. | 2 | 3 | No | Nav | 1
14 | Task 4 - Registering a new user | Make a button to register a user in case the user does not exist. When the user registers, the user can enter their email and password. The information should store into a database where their account will be saved. | 2 | 4 | Yes | Jeff, Tony | 1
15 | Task 7 - Make Login interface | Make the graphical interface user-friendly. Must be able to distinguish each element (login vs. register) and distinguish the various fields (email vs password) | 1 | 2 | Yes | Tony | 1
8 | Task 1 - Missing graphic interface | Make a proper graphic interface for the dashboard. It needs to be easy to follow and navigate. | 1 | 3 | Yes | Lam | 1
10 | Task 2 - Missing Role specification on Dashboard | The dashboard displays the role of the user when they log-in. The role options that are displayed are users and admins. The role is displayed right under the user's name. | 2 | 1 | No | Jeff, Gilbert | 1
19 | Task 9 - Display user's login information | When the user logs into the system, they can see their email displayed. | 2 | 2 | No | Jeff | 1
11
12 | Users can message other users.. |  |  | Conversations using DM can only be seen by people involved in the DM.
13 | Users can join channels
14 | Messages sent in a channel are visible to all users in that channel. |  |  | - Entire message thread is visible in one page - Page hidden to non-participants
15
16 | message storage
17 | admin can create/delete channels
18 | mention other users
19
20 | Base user can log-in into the system into user mode |  |  | - UI includes a field for username and password, button to log in - User has base permissions only once logged in
21 | Admin user can log-in into system into admin mode |  |  | - Graphical interface - username and password - submitting will validate the combination and lead to homepage with the correct permissions
22 | admin can create/delete channels and |  |  | - Graphical interface - graphical element to open a popup that would allow creation and naming of channel - right clicking existing channels shows the option of deleting the channel as well as a confirmation panel
23 | Admin can assign users to channels
24 | All users are greeted by a dashboard/homepage
25